## Dashboard
AI-Powered Smart Municipal Citizen Assistance & Staff Attendance Management System - Executive Dashboard
Overall Completion % |  | Blocked Tasks |  | Critical Issues Open |  | Open Bugs |  | Security Checklist % |  | Deployment Readiness %
0.33333 |  | 0 |  | 2 |  | 1 |  | 0.25 |  | 0.375
Team Workload & Progress Summary | [6 empty] | Module Development Status | [5 empty] | Day-Wise Progress Timeline
Team Member | Assigned Tasks | Completed | Pending | Blocked | Completion % |  | Module Name | Total Tasks | Completed | Pending | Blocked | Completion % | Day | Total Tasks | Completed | Completion %
Minha Palakkathodi | 6 | 2 | 4 | 0 | 0.33333 |  | Backend | 11 | 3 | 8 | 0 | 0.27273 | Sprint 0 | 5 | 5 | 1
Adithyan N | 20 | 8 | 12 | 0 | 0.4 |  | Frontend | 18 | 7 | 11 | 0 | 0.38889 | Day 1 | 7 | 7 | 1
Fathima Hana | 6 | 4 | 2 | 0 | 0.66667 |  | Database | 6 | 4 | 2 | 0 | 0.66667 | Day 2 | 5 | 5 | 1
Muhammad Sanish | 13 | 5 | 8 | 0 | 0.38462 |  | AI | 5 | 0 | 5 | 0 | 0 | Day 3 | 6 | 2 | 0.33333
Fadi Ahmed | 7 | 0 | 7 | 0 | 0 |  | Face Recognition | 7 | 0 | 7 | 0 | 0 | Day 4 | 7 | 0 | 0
Muhammed Sadik KT | 5 | 0 | 5 | 0 | 0 |  | Documentation & QA | 6 | 2 | 4 | 0 | 0.33333 | Day 5 | 11 | 0 | 0
[7 empty] | Infrastructure | 4 | 3 | 1 | 0 | 0.75 | Day 6 | 11 | 0 | 0
Task ID | Module | Task Name | Assigned To | Priority | Status | Progress % | Due Day | Dependency | Testing Status | Security Status | Remarks |  | Day 7 | 5 | 0 | 0
TASK-INF-001 | Infrastructure | MongoDB Atlas Setup | Adithyan N | Critical | Completed | 1 | Sprint 0 | None | Completed | Completed | Admin controls configured and database connection verified
TASK-INF-002 | Infrastructure | Environment Configuration | Muhammad Sanish | High | Completed | 1 | Sprint 0 | None | Completed | Completed | No secrets committed, configuration structure validated
TASK-INF-003 | Infrastructure | Logging Infrastructure Setup | Muhammad Sanish | Medium | Completed | 1 | Day 1 | TASK-INF-002 | Completed | Completed | Sensitive data redacted in Winston streams
TASK-INF-004 | Infrastructure | Deployment Environment Preparation | Adithyan N | Medium | Not Started | 0 | Day 7 | None | Pending | Pending | Deployment scripts drafted, hosting environments initialized
TASK-FE-001 | Frontend | React Setup | Adithyan N | High | Completed | 1 | Sprint 0 | None | Completed | Completed | Vite React scaffolded with standard directory layout
TASK-FE-002 | Frontend | Tailwind Setup | Adithyan N | High | Completed | 1 | Sprint 0 | TASK-FE-001 | Completed | Completed | Tailwind configuration, colors, and typography set up
TASK-FE-003 | Frontend | Routing | Adithyan N | High | Completed | 1 | Day 1 | TASK-FE-001 | Completed | Completed | Browser router routes setup, layout routes configured
TASK-FE-004 | Frontend | Protected Routes | Adithyan N | High | Completed | 1 | Day 1 | TASK-FE-003 | Completed | Completed | Client RBAC guard integrated with token decoder
TASK-FE-005 | Frontend | Axios Setup | Adithyan N | High | Completed | 1 | Day 1 | None | Completed | Completed | JWT interceptor setup, retry limits configured
TASK-FE-006 | Frontend | Authentication UI | Adithyan N | High | Completed | 1 | Day 2 | TASK-FE-004 | Completed | Completed | Secure cookie setup and form validations active
TASK-FE-007 | Frontend | Citizen Dashboard | Adithyan N | High | Completed | 1 | Day 2 | TASK-FE-004 | Completed | Completed | Overview console with responsive metrics cards active
TASK-FE-008 | Frontend | Complaint UI | Adithyan N | High | In Progress | 0.5 | Day 3 | TASK-FE-007 | Pending | Pending | Input sanitizations in progress, UI layout complete
TASK-FE-009 | Frontend | File Tracking UI | Adithyan N | Medium | In Progress | 0.5 | Day 3 | TASK-FE-005 | Pending | Pending | Timeline progress bar rendering in progress
TASK-FE-010 | Frontend | Feedback UI | Adithyan N | Medium | Not Started | 0 | Day 5 | TASK-FE-008 | Pending | Pending | Satisfaction ratings form mockup completed
TASK-FE-011 | Frontend | Staff Dashboard UI | Adithyan N | High | Not Started | 0 | Day 4 | TASK-FE-004 | Pending | Pending | Employee operations view blueprint set
TASK-FE-012 | Frontend | Attendance UI | Adithyan N | High | Not Started | 0 | Day 4 | TASK-FE-011 | Pending | Pending | Liveness scan layout mock complete
TASK-FE-013 | Frontend | Chatbot UI | Adithyan N | Medium | Not Started | 0 | Day 5 | TASK-FE-005 | Pending | Pending | Gemini chat console overlay designed
TASK-FE-014 | Frontend | Admin Dashboard | Adithyan N | High | Not Started | 0 | Day 5 | TASK-FE-004 | Pending | Pending | Audit logs reviewer views prepared
TASK-FE-015 | Frontend | Notifications UI | Adithyan N | Medium | Not Started | 0 | Day 6 | TASK-FE-005 | Pending | Pending | Dynamic web toasts configuration ready
TASK-FE-016 | Frontend | Responsive Fixes | Adithyan N | Medium | Not Started | 0 | Day 6 | TASK-FE-014 | Pending | Pending | Mobile views checking strategy defined
TASK-FE-017 | Frontend | Integration | Adithyan N | High | Not Started | 0 | Day 6 | TASK-FE-015 | Pending | Pending | All endpoints integration mapping checklist
TASK-FE-018 | Frontend | Final UI Testing | Adithyan N | High | Not Started | 0 | Day 7 | TASK-FE-017 | Pending | Pending | QA Visual signoff template configured
TASK-BE-001 | Backend | Express Setup | Muhammad Sanish | Critical | Completed | 1 | Day 1 | TASK-INF-002 | Completed | Completed | Winston logger active and CORS rules applied
TASK-BE-002 | Backend | JWT Authentication | Muhammad Sanish | Critical | Completed | 1 | Day 2 | TASK-BE-001 | Completed | Completed | Bcrypt hashed passwords verified on register
TASK-BE-003 | Backend | RBAC | Muhammad Sanish | Critical | Completed | 1 | Day 2 | TASK-BE-002 | Completed | Completed | Token payload checks for Citizen, Staff, Admin active
TASK-BE-004 | Backend | Complaint APIs | Muhammad Sanish | High | Review | 0.8 | Day 3 | TASK-BE-003 | Completed | Pending | Transaction logs active, code complete, undergoing review
TASK-BE-005 | Backend | File Tracking APIs | Muhammad Sanish | Medium | Review | 0.8 | Day 3 | TASK-BE-003 | Completed | Pending | Escaped tracking strings active, under API review
TASK-BE-006 | Backend | Attendance APIs | Muhammad Sanish | High | Not Started | 0 | Day 4 | TASK-BE-003 | Pending | Pending | Secure verification punches adapter specifications ready
TASK-BE-007 | Backend | Feedback APIs | Muhammad Sanish | Medium | Not Started | 0 | Day 5 | TASK-BE-004 | Pending | Pending | Complaints lock logic active draft
TASK-BE-008 | Backend | Admin APIs | Muhammad Sanish | High | Not Started | 0 | Day 5 | TASK-BE-003 | Pending | Pending | Admin RBAC validation middlewares declared
TASK-BE-009 | Backend | Audit Logging | Muhammad Sanish | High | Not Started | 0 | Day 6 | TASK-BE-001 | Pending | Pending | Log write validations schema prepared
TASK-BE-010 | Backend | Middleware | Muhammad Sanish | High | Not Started | 0 | Day 6 | TASK-BE-001 | Pending | Pending | Standard middlewares pipeline mapped
TASK-BE-011 | Backend | Security Middleware | Muhammad Sanish | Critical | Not Started | 0 | Day 6 | TASK-BE-001 | Pending | Pending | SameSite token configurations specified
TASK-DB-001 | Database | Core Schema Creation | Fathima Hana | Critical | Completed | 1 | Sprint 0 | TASK-INF-001 | Completed | Completed | Support: Adithyan N. Constraints loaded and DB connection active
TASK-DB-002 | Database | Mongoose Models | Fathima Hana | Critical | Completed | 1 | Day 1 | TASK-DB-001 | Completed | Completed | Support: Adithyan N. Unique key bounds and validators active
TASK-DB-003 | Database | Relationships | Fathima Hana | High | Completed | 1 | Day 3 | TASK-DB-002 | Completed | Completed | Support: Adithyan N. Model referencing setup and verified
TASK-DB-004 | Database | Indexing | Fathima Hana | Medium | Completed | 1 | Day 3 | TASK-DB-002 | Completed | Completed | Support: Adithyan N. Indexes configured, query execution fast
TASK-DB-005 | Database | Validation | Fathima Hana | High | Not Started | 0 | Day 6 | TASK-DB-002 | Pending | Pending | Support: Adithyan N. Format checks drafted
TASK-DB-006 | Database | Query Optimization | Fathima Hana | Medium | Not Started | 0 | Day 6 | TASK-DB-004 | Pending | Pending | Support: Adithyan N. Query optimization strategy defined
TASK-AI-001 | AI | Gemini Chatbot | Muhammed Sadik KT | High | Not Started | 0 | Day 5 | None | Pending | Pending | RAG context bounds applied
TASK-AI-002 | AI | OCR | Muhammed Sadik KT | Medium | Not Started | 0 | Day 5 | None | Pending | Pending | Secure local storage sandbox specs
TASK-AI-003 | AI | AI APIs | Muhammed Sadik KT | High | Not Started | 0 | Day 5 | None | Pending | Pending | Secure credentials configuration detailed
TASK-AI-004 | AI | Prompt Engineering | Muhammed Sadik KT | Medium | Not Started | 0 | Day 5 | TASK-AI-001 | Pending | Pending | Prompt injection guards drafted
TASK-AI-005 | AI | Face Recognition Core Implementation | Muhammed Sadik KT | Critical | Not Started | 0 | Day 4 | None | Pending | Pending | Volatile RAM comparison model designed
TASK-FR-001 | Face Recognition | Dataset Collection | Fadi Ahmed | Medium | Not Started | 0 | Day 4 | None | Pending | Pending | Offline template protection standards set
TASK-FR-002 | Face Recognition | Prototype Refinement | Fadi Ahmed | High | Not Started | 0 | Day 4 | TASK-AI-005 | Pending | Pending | Anti-spoofing test frameworks ready
TASK-FR-003 | Face Recognition | Camera Integration Testing | Fadi Ahmed | Medium | Not Started | 0 | Day 4 | None | Pending | Pending | Zero frame storage validation script written
TASK-FR-004 | Face Recognition | Attendance Workflow Testing | Fadi Ahmed | High | Not Started | 0 | Day 5 | TASK-FR-003 | Pending | Pending | Consent constraints gating check template
TASK-FR-005 | Face Recognition | Recognition Accuracy Testing | Fadi Ahmed | High | Not Started | 0 | Day 5 | TASK-FR-002 | Pending | Pending | Robustness audit report format ready
TASK-FR-006 | Face Recognition | Cross-Browser Camera Testing | Fadi Ahmed | Medium | Not Started | 0 | Day 6 | TASK-FR-003 | Pending | Pending | Web permissions tests blueprint
TASK-FR-007 | Face Recognition | System Integration Testing | Fadi Ahmed | High | Not Started | 0 | Day 6 | TASK-FR-004 | Pending | Pending | RBAC boundary check verified
TASK-QA-001 | Documentation & QA | Test Cases | Minha Palakkathodi | High | Completed | 1 | Day 2 | None | Completed | Completed | Validation schedules and manual test logs created
TASK-QA-002 | Documentation & QA | Traceability Matrix | Minha Palakkathodi | High | Completed | 1 | Day 1 | None | Completed | Completed | SRS mappings verified and formatted
TASK-QA-003 | Documentation & QA | QA Reports | Minha Palakkathodi | Medium | Not Started | 0 | Day 6 | None | Pending | Pending | Sprint review reports templates prepared
TASK-QA-004 | Documentation & QA | UAT | Minha Palakkathodi | High | Not Started | 0 | Day 7 | None | Pending | Pending | Acceptance signs template setup
TASK-QA-005 | Documentation & QA | Handover Documentation | Minha Palakkathodi | High | Not Started | 0 | Day 7 | None | Pending | Pending | Official handoff portfolio templates drafted
TASK-QA-006 | Documentation & QA | Documentation Updates | Minha Palakkathodi | Medium | Not Started | 0 | Day 7 | None | Pending | Pending | Final directory inventory check template

## Kanban Board
AI-Powered Smart Municipal Kanban Board (Status Flow Tracker)
| Project Name: | Smart Municipal Assistance MVP |  | Enterprise Lead: | Adithyan N & PMO Team |  | Target Milestone: | 1-Week Rapid MVP Release
Backlog / Future |  |  | Not Started |  |  | In Progress |  |  | Under Review |  |  | Completed
Task ID | Task Name | Assigned To | Task ID | Task Name | Assigned To | Task ID | Task Name | Assigned To | Task ID | Task Name | Assigned To | Task ID | Task Name | Assigned To
|  |  | TASK-INF-004 | Deployment Environment Preparation | Adithyan N | TASK-FE-008 | Complaint UI | Adithyan N | TASK-BE-004 | Complaint APIs | Muhammad Sanish | TASK-INF-001 | MongoDB Atlas Setup | Adithyan N
|  |  | TASK-FE-010 | Feedback UI | Adithyan N | TASK-FE-009 | File Tracking UI | Adithyan N | TASK-BE-005 | File Tracking APIs | Muhammad Sanish | TASK-INF-002 | Environment Configuration | Muhammad Sanish
|  |  | TASK-FE-011 | Staff Dashboard UI | Adithyan N | [6 empty] | TASK-INF-003 | Logging Infrastructure Setup | Muhammad Sanish
|  |  | TASK-FE-012 | Attendance UI | Adithyan N | [6 empty] | TASK-FE-001 | React Setup | Adithyan N
|  |  | TASK-FE-013 | Chatbot UI | Adithyan N | [6 empty] | TASK-FE-002 | Tailwind Setup | Adithyan N
|  |  | TASK-FE-014 | Admin Dashboard | Adithyan N | [6 empty] | TASK-FE-003 | Routing | Adithyan N
|  |  | TASK-FE-015 | Notifications UI | Adithyan N | [6 empty] | TASK-FE-004 | Protected Routes | Adithyan N
|  |  | TASK-FE-016 | Responsive Fixes | Adithyan N | [6 empty] | TASK-FE-005 | Axios Setup | Adithyan N
|  |  | TASK-FE-017 | Integration | Adithyan N | [6 empty] | TASK-FE-006 | Authentication UI | Adithyan N
|  |  | TASK-FE-018 | Final UI Testing | Adithyan N | [6 empty] | TASK-FE-007 | Citizen Dashboard | Adithyan N
|  |  | TASK-BE-006 | Attendance APIs | Muhammad Sanish | [6 empty] | TASK-BE-001 | Express Setup | Muhammad Sanish
|  |  | TASK-BE-007 | Feedback APIs | Muhammad Sanish | [6 empty] | TASK-BE-002 | JWT Authentication | Muhammad Sanish
|  |  | TASK-BE-008 | Admin APIs | Muhammad Sanish | [6 empty] | TASK-BE-003 | RBAC | Muhammad Sanish
|  |  | TASK-BE-009 | Audit Logging | Muhammad Sanish | [6 empty] | TASK-DB-001 | Core Schema Creation | Fathima Hana
|  |  | TASK-BE-010 | Middleware | Muhammad Sanish | [6 empty] | TASK-DB-002 | Mongoose Models | Fathima Hana
|  |  | TASK-BE-011 | Security Middleware | Muhammad Sanish | [6 empty] | TASK-DB-003 | Relationships | Fathima Hana
|  |  | TASK-DB-005 | Validation | Fathima Hana | [6 empty] | TASK-DB-004 | Indexing | Fathima Hana
|  |  | TASK-DB-006 | Query Optimization | Fathima Hana | [6 empty] | TASK-QA-001 | Test Cases | Minha Palakkathodi
|  |  | TASK-AI-001 | Gemini Chatbot | Muhammed Sadik KT | [6 empty] | TASK-QA-002 | Traceability Matrix | Minha Palakkathodi
|  |  | TASK-AI-002 | OCR | Muhammed Sadik KT
|  |  | TASK-AI-003 | AI APIs | Muhammed Sadik KT
|  |  | TASK-AI-004 | Prompt Engineering | Muhammed Sadik KT
|  |  | TASK-AI-005 | Face Recognition Core Implementation | Muhammed Sadik KT
|  |  | TASK-FR-001 | Dataset Collection | Fadi Ahmed
|  |  | TASK-FR-002 | Prototype Refinement | Fadi Ahmed
|  |  | TASK-FR-003 | Camera Integration Testing | Fadi Ahmed
|  |  | TASK-FR-004 | Attendance Workflow Testing | Fadi Ahmed
|  |  | TASK-FR-005 | Recognition Accuracy Testing | Fadi Ahmed
|  |  | TASK-FR-006 | Cross-Browser Camera Testing | Fadi Ahmed
|  |  | TASK-FR-007 | System Integration Testing | Fadi Ahmed
|  |  | TASK-QA-003 | QA Reports | Minha Palakkathodi
|  |  | TASK-QA-004 | UAT | Minha Palakkathodi
|  |  | TASK-QA-005 | Handover Documentation | Minha Palakkathodi
|  |  | TASK-QA-006 | Documentation Updates | Minha Palakkathodi

## Sprint 0
Gantt Timeline Plan - Sprint 0 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-INF-001 | MongoDB Atlas Setup | Adithyan N | Critical | None | Completed | Live MongoDB Atlas cluster with restricted access policies | Yes | Yes | Admin controls configured and database connection verified
TASK-INF-002 | Environment Configuration | Muhammad Sanish | High | None | Completed | .env.example environment configuration template | Yes | Yes | No secrets committed, configuration structure validated
TASK-FE-001 | React Setup | Adithyan N | High | None | Completed | React application project template structure initialized | Yes | Yes | Vite React scaffolded with standard directory layout
TASK-FE-002 | Tailwind Setup | Adithyan N | High | TASK-FE-001 | Completed | Tailwind CSS utility config and design theme tokens loaded | Yes | Yes | Tailwind configuration, colors, and typography set up
TASK-DB-001 | Core Schema Creation | Fathima Hana | Critical | TASK-INF-001 | Completed | Initial collections setup scripts (14 mandatory schemas) | Yes | Yes | Support: Adithyan N. Constraints loaded and DB connection active

## Day 1
Gantt Timeline Plan - Day 1 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-INF-003 | Logging Infrastructure Setup | Muhammad Sanish | Medium | TASK-INF-002 | Completed | Winston/Morgan logger script with data redaction middleware | Yes | Yes | Sensitive data redacted in Winston streams
TASK-FE-003 | Routing | Adithyan N | High | TASK-FE-001 | Completed | React Router routes paths configuration mappings | Yes | Yes | Browser router routes setup, layout routes configured
TASK-FE-004 | Protected Routes | Adithyan N | High | TASK-FE-003 | Completed | Route guard elements validation checking tokens | Yes | Yes | Client RBAC guard integrated with token decoder
TASK-FE-005 | Axios Setup | Adithyan N | High | None | Completed | Axios client instance configured with auth header interceptors | Yes | Yes | JWT interceptor setup, retry limits configured
TASK-BE-001 | Express Setup | Muhammad Sanish | Critical | TASK-INF-002 | Completed | Scaffolded Express app configured with helmet CORS rates filters | Yes | Yes | Winston logger active and CORS rules applied
TASK-DB-002 | Mongoose Models | Fathima Hana | Critical | TASK-DB-001 | Completed | Mongoose schemas definitions users, complaints, tracking | Yes | Yes | Support: Adithyan N. Unique key bounds and validators active
TASK-QA-002 | Traceability Matrix | Minha Palakkathodi | High | None | Completed | Requirements validation spreadsheet mapping models to routes | Yes | Yes | SRS mappings verified and formatted

## Day 2
Gantt Timeline Plan - Day 2 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-FE-006 | Authentication UI | Adithyan N | High | TASK-FE-004 | Completed | Responsive login, register, and password reset form grids | Yes | Yes | Secure cookie setup and form validations active
TASK-FE-007 | Citizen Dashboard | Adithyan N | High | TASK-FE-004 | Completed | Citizen portal layout display grids with ticket log table | Yes | Yes | Overview console with responsive metrics cards active
TASK-BE-002 | JWT Authentication | Muhammad Sanish | Critical | TASK-BE-001 | Completed | Signup, Login, and Session controller routers with tokens | Yes | Yes | Bcrypt hashed passwords verified on register
TASK-BE-003 | RBAC | Muhammad Sanish | Critical | TASK-BE-002 | Completed | Authorization middleware gating api endpoints matching roles | Yes | Yes | Token payload checks for Citizen, Staff, Admin active
TASK-QA-001 | Test Cases | Minha Palakkathodi | High | None | Completed | Functional test logs templates citizen/staff workflows | Yes | Yes | Validation schedules and manual test logs created

## Day 3
Gantt Timeline Plan - Day 3 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-FE-008 | Complaint UI | Adithyan N | High | TASK-FE-007 | In Progress | Grievance registration intakes forms with attachment fields | Yes | Yes | Input sanitizations in progress, UI layout complete
TASK-FE-009 | File Tracking UI | Adithyan N | Medium | TASK-FE-005 | In Progress | Public lookup files status visual progress timelines tracker | Yes | Yes | Timeline progress bar rendering in progress
TASK-BE-004 | Complaint APIs | Muhammad Sanish | High | TASK-BE-003 | Review | GET / POST / PUT complaints routers with ownership filters | Yes | Yes | Transaction logs active, code complete, undergoing review
TASK-BE-005 | File Tracking APIs | Muhammad Sanish | Medium | TASK-BE-003 | Review | Public tracking API endpoints hiding restricted properties | Yes | Yes | Escaped tracking strings active, under API review
TASK-DB-003 | Relationships | Fathima Hana | High | TASK-DB-002 | Completed | Foreign references configurations between users and complaints | Yes | Yes | Support: Adithyan N. Model referencing setup and verified
TASK-DB-004 | Indexing | Fathima Hana | Medium | TASK-DB-002 | Completed | Unique indices on user IDs and geospatial tags on complaints | Yes | Yes | Support: Adithyan N. Indexes configured, query execution fast

## Day 4
Gantt Timeline Plan - Day 4 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-FE-011 | Staff Dashboard UI | Adithyan N | High | TASK-FE-004 | Not Started | Staff operations control tables and status assignment buttons | Yes | Yes | Employee operations view blueprint set
TASK-FE-012 | Attendance UI | Adithyan N | High | TASK-FE-011 | Not Started | Consent prompt and webcam feed canvas punch frames | Yes | Yes | Liveness scan layout mock complete
TASK-BE-006 | Attendance APIs | Muhammad Sanish | High | TASK-BE-003 | Not Started | Consent verification punches and fallbacks endpoints adapters | Yes | Yes | Secure verification punches adapter specifications ready
TASK-AI-005 | Face Recognition Core Implementation | Muhammed Sadik KT | Critical | None | Not Started | Python face matching algorithms calculating liveness scores | Yes | Yes | Volatile RAM comparison model designed
TASK-FR-001 | Dataset Collection | Fadi Ahmed | Medium | None | Not Started | Standardized profile template datasets for staff registration calibrator | Yes | Yes | Offline template protection standards set
TASK-FR-002 | Prototype Refinement | Fadi Ahmed | High | TASK-AI-005 | Not Started | Optimized landmarks matrix comparison module testing files | Yes | Yes | Anti-spoofing test frameworks ready
TASK-FR-003 | Camera Integration Testing | Fadi Ahmed | Medium | None | Not Started | HTML webcam access wrapper components tests reports | Yes | Yes | Zero frame storage validation script written

## Day 5
Gantt Timeline Plan - Day 5 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-FE-010 | Feedback UI | Adithyan N | Medium | TASK-FE-008 | Not Started | Satisfaction ratings form controls locking completed complaints | Yes | Yes | Satisfaction ratings form mockup completed
TASK-FE-013 | Chatbot UI | Adithyan N | Medium | TASK-FE-005 | Not Started | Chat container overlays with scrolling dialog logs interface | Yes | Yes | Gemini chat console overlay designed
TASK-FE-014 | Admin Dashboard | Adithyan N | High | TASK-FE-004 | Not Started | User management console and Audit system dashboard panels | Yes | Yes | Audit logs reviewer views prepared
TASK-BE-007 | Feedback APIs | Muhammad Sanish | Medium | TASK-BE-004 | Not Started | Grievance feedback ratings submission routers locking ticket | Yes | Yes | Complaints lock logic active draft
TASK-BE-008 | Admin APIs | Muhammad Sanish | High | TASK-BE-003 | Not Started | Administrative configs and system parameter modifications APIs | Yes | Yes | Admin RBAC validation middlewares declared
TASK-AI-001 | Gemini Chatbot | Muhammed Sadik KT | High | None | Not Started | Grounded chat orchestrator wrapper using Gemini APIs models | Yes | Yes | RAG context bounds applied
TASK-AI-002 | OCR | Muhammed Sadik KT | Medium | None | Not Started | PDF/Image metadata scanner extracting doc credentials details | Yes | Yes | Secure local storage sandbox specs
TASK-AI-003 | AI APIs | Muhammed Sadik KT | High | None | Not Started | Microservice endpoints parsing citizen attachments and query logs | Yes | Yes | Secure credentials configuration detailed
TASK-AI-004 | Prompt Engineering | Muhammed Sadik KT | Medium | TASK-AI-001 | Not Started | Prompt system blueprints grounding chatbot in municipality docs | Yes | Yes | Prompt injection guards drafted
TASK-FR-004 | Attendance Workflow Testing | Fadi Ahmed | High | TASK-FR-003 | Not Started | Webcam punch validation tracing logs check-ins | Yes | Yes | Consent constraints gating check template
TASK-FR-005 | Recognition Accuracy Testing | Fadi Ahmed | High | TASK-FR-002 | Not Started | Accuracy metrics checking FAR and FRR scales results log | Yes | Yes | Robustness audit report format ready

## Day 6
Gantt Timeline Plan - Day 6 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-FE-015 | Notifications UI | Adithyan N | Medium | TASK-FE-005 | Not Started | Alert toasts dialogs and global notifications dropdown list | Yes | Yes | Dynamic web toasts configuration ready
TASK-FE-016 | Responsive Fixes | Adithyan N | Medium | TASK-FE-014 | Not Started | CSS media queries patches verifying mobile responsiveness | Yes | Yes | Mobile views checking strategy defined
TASK-FE-017 | Integration | Adithyan N | High | TASK-FE-015 | Not Started | Frontend view layouts wired to active backend API endpoints | Yes | Yes | All endpoints integration mapping checklist
TASK-BE-009 | Audit Logging | Muhammad Sanish | High | TASK-BE-001 | Not Started | Transactional logger tracking key security database modifications | Yes | Yes | Log write validations schema prepared
TASK-BE-010 | Middleware | Muhammad Sanish | High | TASK-BE-001 | Not Started | Centralized error handlers and request ID injector scripts | Yes | Yes | Standard middlewares pipeline mapped
TASK-BE-011 | Security Middleware | Muhammad Sanish | Critical | TASK-BE-001 | Not Started | Anti-NoSQL injections and CAPTCHA validators middlewares | Yes | Yes | SameSite token configurations specified
TASK-DB-005 | Validation | Fathima Hana | High | TASK-DB-002 | Not Started | Custom validation functions sanitizing inputs before DB write | Yes | Yes | Support: Adithyan N. Format checks drafted
TASK-DB-006 | Query Optimization | Fathima Hana | Medium | TASK-DB-004 | Not Started | Explain query audit logs verifying efficient index mappings | Yes | Yes | Support: Adithyan N. Query optimization strategy defined
TASK-FR-006 | Cross-Browser Camera Testing | Fadi Ahmed | Medium | TASK-FR-003 | Not Started | Webcam rendering log on Safari, Firefox, Chrome, Edge | Yes | Yes | Web permissions tests blueprint
TASK-FR-007 | System Integration Testing | Fadi Ahmed | High | TASK-FR-004 | Not Started | Biometrics validation checklist verifying dashboard updates logs | Yes | Yes | RBAC boundary check verified
TASK-QA-003 | QA Reports | Minha Palakkathodi | Medium | None | Not Started | Completed QA pass summaries checklist log sheet | Yes | Yes | Sprint review reports templates prepared

## Day 7
Gantt Timeline Plan - Day 7 Schedule & Tasks
Task ID | Task Name | Assigned To | Priority | Dependency | Status | Deliverable | Testing Required | Security Check Required | Remarks
TASK-INF-004 | Deployment Environment Preparation | Adithyan N | Medium | None | Not Started | Render/Vercel production environment config sheets | Yes | Yes | Deployment scripts drafted, hosting environments initialized
TASK-FE-018 | Final UI Testing | Adithyan N | High | TASK-FE-017 | Not Started | E2E user interface visual checking verification report | Yes | Yes | QA Visual signoff template configured
TASK-QA-004 | UAT | Minha Palakkathodi | High | None | Not Started | User acceptance tracking forms templates validation | Yes | Yes | Acceptance signs template setup
TASK-QA-005 | Handover Documentation | Minha Palakkathodi | High | None | Not Started | Consolidated developer guide and handover checklist documentation | Yes | Yes | Official handoff portfolio templates drafted
TASK-QA-006 | Documentation Updates | Minha Palakkathodi | Medium | None | Not Started | Updated README and master documents folders checklists | Yes | Yes | Final directory inventory check template

## Backend Tasks
Backend Tasks (Module Lead: Muhammad Sanish)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-BE-001 | Express Setup | Muhammad Sanish | Critical | Completed | Day 1 | TASK-INF-002 | Completed | Winston logger active and CORS rules applied
TASK-BE-002 | JWT Authentication | Muhammad Sanish | Critical | Completed | Day 2 | TASK-BE-001 | Completed | Bcrypt hashed passwords verified on register
TASK-BE-003 | RBAC | Muhammad Sanish | Critical | Completed | Day 2 | TASK-BE-002 | Completed | Token payload checks for Citizen, Staff, Admin active
TASK-BE-004 | Complaint APIs | Muhammad Sanish | High | Review | Day 3 | TASK-BE-003 | Completed | Transaction logs active, code complete, undergoing review
TASK-BE-005 | File Tracking APIs | Muhammad Sanish | Medium | Review | Day 3 | TASK-BE-003 | Completed | Escaped tracking strings active, under API review
TASK-BE-006 | Attendance APIs | Muhammad Sanish | High | Not Started | Day 4 | TASK-BE-003 | Pending | Secure verification punches adapter specifications ready
TASK-BE-007 | Feedback APIs | Muhammad Sanish | Medium | Not Started | Day 5 | TASK-BE-004 | Pending | Complaints lock logic active draft
TASK-BE-008 | Admin APIs | Muhammad Sanish | High | Not Started | Day 5 | TASK-BE-003 | Pending | Admin RBAC validation middlewares declared
TASK-BE-009 | Audit Logging | Muhammad Sanish | High | Not Started | Day 6 | TASK-BE-001 | Pending | Log write validations schema prepared
TASK-BE-010 | Middleware | Muhammad Sanish | High | Not Started | Day 6 | TASK-BE-001 | Pending | Standard middlewares pipeline mapped
TASK-BE-011 | Security Middleware | Muhammad Sanish | Critical | Not Started | Day 6 | TASK-BE-001 | Pending | SameSite token configurations specified

## Frontend Tasks
Frontend Tasks (Module Lead: Adithyan N)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-FE-001 | React Setup | Adithyan N | High | Completed | Sprint 0 | None | Completed | Vite React scaffolded with standard directory layout
TASK-FE-002 | Tailwind Setup | Adithyan N | High | Completed | Sprint 0 | TASK-FE-001 | Completed | Tailwind configuration, colors, and typography set up
TASK-FE-003 | Routing | Adithyan N | High | Completed | Day 1 | TASK-FE-001 | Completed | Browser router routes setup, layout routes configured
TASK-FE-004 | Protected Routes | Adithyan N | High | Completed | Day 1 | TASK-FE-003 | Completed | Client RBAC guard integrated with token decoder
TASK-FE-005 | Axios Setup | Adithyan N | High | Completed | Day 1 | None | Completed | JWT interceptor setup, retry limits configured
TASK-FE-006 | Authentication UI | Adithyan N | High | Completed | Day 2 | TASK-FE-004 | Completed | Secure cookie setup and form validations active
TASK-FE-007 | Citizen Dashboard | Adithyan N | High | Completed | Day 2 | TASK-FE-004 | Completed | Overview console with responsive metrics cards active
TASK-FE-008 | Complaint UI | Adithyan N | High | In Progress | Day 3 | TASK-FE-007 | Pending | Input sanitizations in progress, UI layout complete
TASK-FE-009 | File Tracking UI | Adithyan N | Medium | In Progress | Day 3 | TASK-FE-005 | Pending | Timeline progress bar rendering in progress
TASK-FE-010 | Feedback UI | Adithyan N | Medium | Not Started | Day 5 | TASK-FE-008 | Pending | Satisfaction ratings form mockup completed
TASK-FE-011 | Staff Dashboard UI | Adithyan N | High | Not Started | Day 4 | TASK-FE-004 | Pending | Employee operations view blueprint set
TASK-FE-012 | Attendance UI | Adithyan N | High | Not Started | Day 4 | TASK-FE-011 | Pending | Liveness scan layout mock complete
TASK-FE-013 | Chatbot UI | Adithyan N | Medium | Not Started | Day 5 | TASK-FE-005 | Pending | Gemini chat console overlay designed
TASK-FE-014 | Admin Dashboard | Adithyan N | High | Not Started | Day 5 | TASK-FE-004 | Pending | Audit logs reviewer views prepared
TASK-FE-015 | Notifications UI | Adithyan N | Medium | Not Started | Day 6 | TASK-FE-005 | Pending | Dynamic web toasts configuration ready
TASK-FE-016 | Responsive Fixes | Adithyan N | Medium | Not Started | Day 6 | TASK-FE-014 | Pending | Mobile views checking strategy defined
TASK-FE-017 | Integration | Adithyan N | High | Not Started | Day 6 | TASK-FE-015 | Pending | All endpoints integration mapping checklist
TASK-FE-018 | Final UI Testing | Adithyan N | High | Not Started | Day 7 | TASK-FE-017 | Pending | QA Visual signoff template configured

## Database Tasks
Database Tasks (Module Lead: Fathima Hana)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-DB-001 | Core Schema Creation | Fathima Hana | Critical | Completed | Sprint 0 | TASK-INF-001 | Completed | Support: Adithyan N. Constraints loaded and DB connection active
TASK-DB-002 | Mongoose Models | Fathima Hana | Critical | Completed | Day 1 | TASK-DB-001 | Completed | Support: Adithyan N. Unique key bounds and validators active
TASK-DB-003 | Relationships | Fathima Hana | High | Completed | Day 3 | TASK-DB-002 | Completed | Support: Adithyan N. Model referencing setup and verified
TASK-DB-004 | Indexing | Fathima Hana | Medium | Completed | Day 3 | TASK-DB-002 | Completed | Support: Adithyan N. Indexes configured, query execution fast
TASK-DB-005 | Validation | Fathima Hana | High | Not Started | Day 6 | TASK-DB-002 | Pending | Support: Adithyan N. Format checks drafted
TASK-DB-006 | Query Optimization | Fathima Hana | Medium | Not Started | Day 6 | TASK-DB-004 | Pending | Support: Adithyan N. Query optimization strategy defined

## AI Tasks
AI Tasks (Module Lead: Muhammed Sadik KT)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-AI-001 | Gemini Chatbot | Muhammed Sadik KT | High | Not Started | Day 5 | None | Pending | RAG context bounds applied
TASK-AI-002 | OCR | Muhammed Sadik KT | Medium | Not Started | Day 5 | None | Pending | Secure local storage sandbox specs
TASK-AI-003 | AI APIs | Muhammed Sadik KT | High | Not Started | Day 5 | None | Pending | Secure credentials configuration detailed
TASK-AI-004 | Prompt Engineering | Muhammed Sadik KT | Medium | Not Started | Day 5 | TASK-AI-001 | Pending | Prompt injection guards drafted
TASK-AI-005 | Face Recognition Core Implementation | Muhammed Sadik KT | Critical | Not Started | Day 4 | None | Pending | Volatile RAM comparison model designed

## Face Recognition Tasks
Face Recognition Tasks (Module Lead: Fadi Ahmed)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-FR-001 | Dataset Collection | Fadi Ahmed | Medium | Not Started | Day 4 | None | Pending | Offline template protection standards set
TASK-FR-002 | Prototype Refinement | Fadi Ahmed | High | Not Started | Day 4 | TASK-AI-005 | Pending | Anti-spoofing test frameworks ready
TASK-FR-003 | Camera Integration Testing | Fadi Ahmed | Medium | Not Started | Day 4 | None | Pending | Zero frame storage validation script written
TASK-FR-004 | Attendance Workflow Testing | Fadi Ahmed | High | Not Started | Day 5 | TASK-FR-003 | Pending | Consent constraints gating check template
TASK-FR-005 | Recognition Accuracy Testing | Fadi Ahmed | High | Not Started | Day 5 | TASK-FR-002 | Pending | Robustness audit report format ready
TASK-FR-006 | Cross-Browser Camera Testing | Fadi Ahmed | Medium | Not Started | Day 6 | TASK-FR-003 | Pending | Web permissions tests blueprint
TASK-FR-007 | System Integration Testing | Fadi Ahmed | High | Not Started | Day 6 | TASK-FR-004 | Pending | RBAC boundary check verified

## Documentation & QA Tasks
Documentation & QA Tasks (Module Lead: Minha Palakkathodi)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-QA-001 | Test Cases | Minha Palakkathodi | High | Completed | Day 2 | None | Completed | Validation schedules and manual test logs created
TASK-QA-002 | Traceability Matrix | Minha Palakkathodi | High | Completed | Day 1 | None | Completed | SRS mappings verified and formatted
TASK-QA-003 | QA Reports | Minha Palakkathodi | Medium | Not Started | Day 6 | None | Pending | Sprint review reports templates prepared
TASK-QA-004 | UAT | Minha Palakkathodi | High | Not Started | Day 7 | None | Pending | Acceptance signs template setup
TASK-QA-005 | Handover Documentation | Minha Palakkathodi | High | Not Started | Day 7 | None | Pending | Official handoff portfolio templates drafted
TASK-QA-006 | Documentation Updates | Minha Palakkathodi | Medium | Not Started | Day 7 | None | Pending | Final directory inventory check template

## Infrastructure Tasks
Infrastructure Tasks (Module Lead: Adithyan N + Muhammad Sanish)
Task ID | Task Name | Assigned To | Priority | Status | Due Day | Dependency | Testing Status | Remarks
TASK-INF-001 | MongoDB Atlas Setup | Adithyan N | Critical | Completed | Sprint 0 | None | Completed | Admin controls configured and database connection verified
TASK-INF-002 | Environment Configuration | Muhammad Sanish | High | Completed | Sprint 0 | None | Completed | No secrets committed, configuration structure validated
TASK-INF-003 | Logging Infrastructure Setup | Muhammad Sanish | Medium | Completed | Day 1 | TASK-INF-002 | Completed | Sensitive data redacted in Winston streams
TASK-INF-004 | Deployment Environment Preparation | Adithyan N | Medium | Not Started | Day 7 | None | Pending | Deployment scripts drafted, hosting environments initialized

## Integration Tracker
Cross-Module Integration Point Registry
Integration ID | Source Module | Destination Module | Interface Name | Data Flow Description | Status | Assigned To | Verification Notes
INT-001 | Backend | Database | Database Connection | Express backend connects to MongoDB Atlas using Mongoose | Completed | Muhammad Sanish | Connection successful, connection pooling configured
INT-002 | Frontend | Backend | Auth Handshake | React client login/register payload to Express auth API endpoints | In Progress | Adithyan N | Endpoints created, UI integration in progress
INT-003 | Backend | AI Services | Gemini Chat Proxy | Express server proxies user queries to Gemini RAG service | Not Started | Muhammad Sanish | Gemini wrapper ready, backend routing pending
INT-004 | Backend | AI Services | Liveness punch service | Express server proxies webcam captures to Python biometric service | Not Started | Muhammad Sanish | Python service prototype ready
INT-005 | Frontend | AI Services | Webcam punch feed | React scanner UI uploads face frames to backend | Not Started | Adithyan N | Webcam access prompt completed
INT-006 | Database | AI Services | Vector Store Index | Gemini RAG queries vector index on MongoDB collection | Not Started | Fathima Hana | Index configured, test queries pending

## Bug Tracker
Defect Prevention and QA Bug Tracker
Bug ID | Summary | Module | Steps to Reproduce | Severity | Priority | Status | Assigned To | Found By | Date Found | Date Closed | Target Release | Resolution Notes
BUG-001 | Token expiration causes infinite loop in Axios interceptor | Frontend | 1. Login to client portal. 2. Wait for JWT token to expire. 3. Request fails, interceptor retries indefinitely. | High | High | In Progress | Adithyan N | Minha Palakkathodi | 2026-06-19 |  | v1.0.0-MVP | Fixing axios interceptor retry count logic.

## Security Checklist
Mandatory MVP Security Validation Gates
Control ID | Security Control Requirement | Verification Method / Evidence | Status | Verified By | Target Day
SEC-001 | No plaintext secrets committed. Config retrieved from env. | Code review of configuration modules & environment logs. | Completed | Adithyan N | Sprint 0
SEC-002 | Bcrypt password hashing configured with workload factor >= 10. | Review backend signup logic and test database hashes. | Completed | Adithyan N | Day 2
SEC-003 | JWT tokens set with short expiration limits (< 15 mins). | Examine JWT payload structures and expiry parameters. | Completed | Adithyan N | Day 2
SEC-004 | Resource ownership filter validated at backend layer. | Testing API modifications under multiple authenticated roles. | In Progress | Adithyan N | Day 3
SEC-005 | Upload restrictions gated to PDF/Image formats and < 5MB. | Try uploading arbitrary text/executable files to complain attachments. | Not Started | Adithyan N | Day 3
SEC-006 | Public trackers suppress private remarks & internal logs. | Call tracking endpoint publicly and inspect JSON response. | Not Started | Adithyan N | Day 3
SEC-007 | Biometric consent checked prior to webcam scan access. | Test attendance check-in workflow without setting consent flag. | Not Started | Adithyan N | Day 4
SEC-008 | Zero photo retention in face recognition microservice. | Verify volatile memory execution and check disk file systems. | Not Started | Adithyan N | Day 4
SEC-009 | Gemini prompts locked within municipal context chunks. | Attempt prompt injections to query non-municipal system topics. | Not Started | Adithyan N | Day 5
SEC-010 | Anti-NoSQL injection middleware active on backend. | Send query payloads with operator tags ($gt, $ne, etc.) to APIs. | Not Started | Adithyan N | Day 6
SEC-011 | SameSite, HTTPOnly and Secure flags set on JWT cookies. | Verify response headers set-cookie attributes in browser console. | Not Started | Adithyan N | Day 6
SEC-012 | Immutable S3 backup snapshot locks configured. | Review backup lock policy config and attempt deletion command. | Not Started | Adithyan N | Day 7

## Daily Standup
Daily Scrum Standup Tracker (15 mins Review logs)
Date | Team Member | Yesterday (Completed Tasks) | Today (Planned Tasks) | Blockers / Roadblocks | Present (Yes/No)
2026-06-19 | Minha Palakkathodi | Completed setup steps | Drafting component architecture | None | Yes
2026-06-19 | Adithyan N | Completed setup steps | Drafting component architecture | None | Yes
2026-06-19 | Fathima Hana | Completed setup steps | Drafting component architecture | None | Yes
2026-06-19 | Muhammad Sanish | Completed setup steps | Drafting component architecture | None | Yes
2026-06-19 | Fadi Ahmed | Completed setup steps | Drafting component architecture | None | Yes
2026-06-19 | Muhammed Sadik KT | Completed setup steps | Drafting component architecture | None | Yes

## Team Workload
Resource Allocation and Productivity Tracker
Team Member | Assigned Tasks | Completed | Pending | Blocked | Completion %
Minha Palakkathodi | 6 | 2 | 4 | 0 | 0.33333
Adithyan N | 20 | 8 | 12 | 0 | 0.4
Fathima Hana | 6 | 4 | 2 | 0 | 0.66667
Muhammad Sanish | 13 | 5 | 8 | 0 | 0.38462
Fadi Ahmed | 7 | 0 | 7 | 0 | 0
Muhammed Sadik KT | 5 | 0 | 5 | 0 | 0

## Dependency Tracker
Critical Path Dependency Registry
Dependency ID | Pre-Requisite Task | Dependent Task | Dependency Description | Status | Severity Impact
DEP-001 | TASK-DB-001 (Core Schemas) | TASK-BE-002 (JWT Auth) | Auth controllers require database schema models before coding begins | Resolved | Critical
DEP-002 | TASK-BE-002 (JWT Auth) | TASK-BE-003 (RBAC) | RBAC filters require authenticated JWT session tokens | Resolved | Critical
DEP-003 | TASK-BE-003 (RBAC) | TASK-FE-INF-003 (Route Guards) | React guards require verified role sets from auth tokens | In Progress | Critical
DEP-004 | TASK-DB-002 (Complaints Schema) | TASK-BE-004 (Complaint APIs) | Complaint controller requires complaints schemas | Not Started | High
DEP-005 | TASK-AI-001 (Python Face Service) | TASK-BE-006 (Biometric APIs) | Backend punches depend on liveness scoring output | Not Started | High
DEP-006 | TASK-BE-006 (Biometric APIs) | TASK-FE-005 (Attendance UI) | Webcam punch portal requires attendance APIs | Not Started | High

## Deployment Checklist
MVP Production Launch Readiness Gates
Deployment ID | Launch Readiness Task | Verification Method | Status | Verified By
DEPL-001 | MongoDB Atlas Multi-AZ cluster config | Verify production connection URI and access rules | Completed | Adithyan N
DEPL-002 | Production environment variables loaded | Check config env parameters on hosting targets | Completed | Muhammad Sanish
DEPL-003 | CORS origins allowlist configured | Ensure only frontend URL is allowed in backend middleware | Completed | Muhammad Sanish
DEPL-004 | HTTPS redirection configuration | Confirm HTTP automatically redirects to HTTPS on production | In Progress | Adithyan N
DEPL-005 | Render API Hosting server deploy | Deploy backend service to Render backend web service | Not Started | Muhammad Sanish
DEPL-006 | Vercel Frontend client deploy | Deploy React app and configure production routing on Vercel | Not Started | Adithyan N
DEPL-007 | Turnstile CAPTCHA keys integration | Load live keys to frontend and backend env properties | Not Started | Adithyan N
DEPL-008 | KMS backup encryption setup | Verify encryption keys rotation policies on AWS KMS | Not Started | Fathima Hana

## Risks & Blockers
Project Risk Mitigation Register
Risk ID | Risk Description | Severity Impact | Mitigation Plan Action | Risk Owner | Status
RSK-001 | Delay in database schema finalization | High | Provide early database support from Adithyan N to Fathima Hana to accelerate coding. | Fathima Hana | Mitigated
RSK-002 | Biometric liveness detection accuracy issues | High | Run training calibrations on diverse light settings and support manual PIN fallback. | Muhammed Sadik KT | Open
RSK-003 | Webcam access permission denials on Safari browsers | Medium | Provide detailed user permission guides and visual warning frames. | Adithyan N | Open
RSK-004 | Database backups data loss or tamper events | Critical | Configure AWS S3 Object Lock compliance mode with retention locks. | Fathima Hana | Open
RSK-005 | API endpoints performance drops under parallel loads | Medium | Configure indexing structures and run database query optimizations. | Muhammad Sanish | Open

## Final Handover Checklist
Official Municipality Handover Packages Delivery Checklist
Handover ID | Handover Package / Deliverable | Owner | Status | Remarks / Details
HND-001 | Developer Guide and API Readme Manual | Minha Palakkathodi | Completed | Official handoff documentation template
HND-002 | GitHub Repository Admin Credentials Transfer | Adithyan N | In Progress | Rotating repository administrative keys
HND-003 | MongoDB Atlas Cluster Credentials Transfer | Adithyan N | Not Started | Transfer ownership to client account
HND-004 | Render and Vercel Hosting Administration Credentials | Muhammad Sanish | Not Started | Provide organization administration logins
HND-005 | Escalation Contacts and SLA Matrix Agreement | Minha Palakkathodi | Not Started | Document contacts list and response guidelines
HND-006 | Biometric Data Consent Forms Logs | Minha Palakkathodi | Not Started | Review records against privacy requirements